## How to Use
Risk Register
The Information Security Policy requires a record of identified risks, and this register is that record: every risk the organization identifies, who owns it, how bad it could be, what is being done about it, and who accepted what remains. The other policies in the set feed it. An unfixable vulnerability, an unmeetable backup target, and a vendor risk acceptance all land here. A vendor risk acceptance also stays in the vendor's record (Vendor Risk Management Policy). A risk the organization accepts as a standing position belongs here, whatever its source. A planned deviation from a policy rule, with an end date, is an exception: it belongs in the exception register, and comes here as well when its risk is significant, since only Executive Management may accept that.
How to use it
Adding a risk
Add a row when a risk assessment, an audit, an incident, or day-to-day work identifies a risk. Describe the risk as what could happen, and to what. Give every risk an owner: the person who answers for it, not necessarily the person who fixes it. For an accepted risk, this is the owner the Information Security Policy requires.
Scoring
Score the risk as it stands today, with the controls already in place. Rate likelihood and impact from 1 to 5 using the definitions on the Scales sheet. The risk level is likelihood times impact. The register calculates it and colors it for you.
The significant threshold
A risk level of [15] or higher is a significant risk. The Information Security Lead recommends how a significant risk is handled. Only Executive Management may accept a significant risk (Information Security Policy). The policy leaves the definition of a significant risk to Executive Management. The [15] threshold and the Scales sheet's definitions are this register's starting values: adopting them is how Executive Management makes that definition.
Treatment
Choose a treatment. Treat: reduce the risk with controls. Accept: decide, in writing, to live with it. Avoid: stop doing the thing that creates it. Transfer: pass the cost to insurance or a contract; the risk itself usually stays yours to manage.
Residual risk
Score the residual risk: what remains after the treatment. Judge the risk with the treatment in place. Rate the residual likelihood and residual impact from 1 to 5 using the same Scales definitions. The register multiplies them into the residual risk level. For a treated risk, the residual is what you expect once the plan is done. Record the acceptance when the plan is agreed. Confirm the scores when the work finishes. If the residual landed higher than expected, re-score it and decide again. For an avoided risk, leave the residual scores blank.
Status
Status tracks the plan: Open (no plan yet), In progress (plan underway), Done (plan finished and the residual confirmed), Accepted (living with the risk as scored), and Closed (the risk is retired). For an avoided risk, once the activity that created it has stopped, set its status to Closed.
Acceptance
Acceptance follows the residual risk level: the risk owner accepts a residual below the significant threshold, and Executive Management accepts a residual at or above it. Executive Management also signs the acceptance of any risk whose assessed risk level (the score before treatment) reached the threshold. That way a significant risk is never accepted without Executive Management seeing it. Executive Management may always accept a risk in the owner's place. A High residual (see the Scales sheet) that is accepted rather than treated also goes to Executive Management. Acceptance does not waive a legal, regulatory, or contractual requirement.
The register review
The [Information Security Lead] reviews the register at least [quarterly], and each risk at least annually. At each register review, check for next review dates that have passed, and for due dates that have passed on plans not yet Done. Confirm scores and treatments still hold, and re-score anything that changed. Reconfirm the acceptance of each accepted risk whose next review has come due. Then set each reviewed risk's next review date. The Information Security Policy requires assessments to be repeated at planned intervals and whenever significant changes are proposed or occur.
Housekeeping
This register lists the organization's weaknesses in one place. Store it where only [the Information Security Lead, Executive Management, and the risk owners] can open it. Classify it under the Data Handling Policy. The example rows hold R-001 to R-006. Type your first real risks over them and keep those IDs. Delete any example rows you do not need; new risks still start at R-007. Once an ID has held a real risk, never reuse or renumber it. When a risk is retired, set its status to Closed. Record the retirement date and reason in the treatment plan cell. Blank its next review date and keep the row. The register shows only each risk's current position, so save a dated copy at each register review to keep earlier scores and decisions on record. If your storage keeps version history, that counts. The formulas, dropdowns, and colors run to row [101]. To add more rows, copy the last empty row down. Never type in the two Risk level columns: they fill themselves. If a Risk level cell ever shows a typed number instead of calculating, restore it by copying that column's cell from any empty row. Avoid square brackets in real entries; the yellow highlight keys on them.
Conventions
Text in square brackets marks a starting value or an example: set it to fit the organization, and replace the six example rows with real risks. On the Risk Register sheet those cells are filled pale yellow, and the yellow clears itself as you replace the bracketed text. The Scales sheet defines the scores. The dropdowns on the Risk Register sheet keep entries consistent.
Framework references
This register records the risk assessments and treatment decisions that ISO/IEC 27001:2022 requires (clauses 6.1.2 and 6.1.3). It supports the Govern and Identify functions of the NIST Cybersecurity Framework 2.0 (the Risk Management Strategy category under Govern, and the Risk Assessment category under Identify).
This template is general guidance, not legal advice. It is provided by anoBytes Technology Solutions (anobytes.com) free to adapt for your organization.

## Risk Register
ID | Date identified | Risk (what could happen, and to what) | Affected assets or activities | Risk owner | Likelihood (1-5) | Impact (1-5) | Risk level | Treatment | Treatment plan (what is being done, or why it is accepted) | Due date | Status | Residual likelihood | Residual impact | Residual risk level | Accepted by, and when (Executive Management where either risk level is significant) | Next review
R-001 | [Date] | Example: ransomware encrypts the file server and shared drives after a phishing email is opened, and day-to-day work stops | File server; finance and operations shares | [Head of IT] | 4 | 5 |  | Treat | Isolated backup copies and restore tests (BC/DR plan Section 6.0); phishing awareness training (Information Security Policy Section 3.5) and reporting duties (Acceptable Use Policy); endpoint protection on all devices | [Date] | In progress | 2 | 4 |  | [Name, Executive Management], [date] | [Date]
R-002 | [Date] | Example: the accounting SaaS provider has a multi-day outage during month-end close | Invoicing and payments | [Finance lead] | 3 | 4 |  | Accept | Provider assessed under the Vendor Risk Management Policy; interim workaround in the BC/DR plan worksheet; loss accepted for outages under [3 days] |  | Accepted | 3 | 4 |  | [Name, Executive Management], [date] | [Date]
R-003 | [Date] | Example: a former employee's cloud account stays active after departure and is used to reach customer data | Cloud services; customer data | [Information Security Lead] | 2 | 5 |  | Treat | Access removed immediately on departure and the removal verified (Access Control Policy Sections 3.1 and 3.6); access reviews run quarterly for this system, tighter than the policy requires | [Date] | Done | 1 | 5 |  | [Name, Information Security Lead (risk owner)], [date] | [Date]
R-004 | [Date] | Example: an internet-facing file-transfer server runs software that no longer gets security updates | Legacy file-transfer server | [Head of IT] | 3 | 4 |  | Avoid | Server retired [date]: the software cannot be made safe, so the exposure was removed; transfers moved to the supported cloud service under the Change Management Policy |  | Closed
R-005 | [Date] | Example: a fire or flood in the office destroys computers and network equipment | Office equipment; on-site network | [Operations lead] | 2 | 4 |  | Transfer | Business property insurance covers replacement; recovery steps in the BC/DR plan's Loss of a Site runbook (Section 7.3); interim workarounds in the BC/DR plan worksheet | [Date] | Done | 2 | 2 |  | [Name, Operations lead (risk owner)], [date] | [Date]
R-006 | [Date] | Example: an attacker impersonating a supplier emails new bank details, and a payment goes to the attacker's account | Supplier payments; accounts payable | [Finance lead] | 3 | 4 |  |  |  |  | Open |  |  |  |  | [Date]

## Scales
Likelihood |  | Impact
1 | Rare: hard to imagine happening in the next few years | 1 | Minor: an inconvenience; no real cost or exposure
2 | Unlikely: could happen, but probably will not in the next 12 months | 2 | Limited: some cost or delay; contained quickly
3 | Possible: could well happen in the next 12 months | 3 | Moderate: real money, lost time, or a small data exposure
4 | Likely: expected to happen in the next 12 months | 4 | Major: serious cost, a legal, regulatory, or contractual breach, or a large data exposure
5 | Almost certain: happening now, or expected more than once in the next 12 months | 5 | Severe: threatens the business, its customers, or its obligations
Risk level = likelihood x impact
1-4 | Low: manage in normal work; review annually
5-9 | Moderate: assign a plan; review at each register review
10-14 | High: treat promptly, or escalate the acceptance to Executive Management; the Information Security Lead tracks it; review at each register review
[15]-25 | Significant: only Executive Management may accept it (Information Security Policy); review at each register review
Set the [15] threshold, and these bands, to match what Executive Management defines as significant. The Information Security Policy leaves that definition to Executive Management. If you change the threshold or the bands, also update the color rules on the Risk Register sheet's two Risk level columns. When in doubt about a risk, treat it as significant. A risk with impact 5 deserves the Information Security Lead's attention whatever its level.